## Sheet1
Sl no | Phase | Task | Description | Est. Hours
1 | Requirement Analysis & Planning | Requirement Gathering | Understanding legacy system structure and target framework | 8
|  | Feasibility Study | Analyze what parts can be modernized via AI | 6
|  | Architecture Planning | Define backend & frontend folder structures, API contracts | 6
2 | Frontend Development | UI Design | High-level wireframes & screens for input/upload and results | 6
|  | React Frontend Setup | Initializing folder structure, routing, theming | 4
|  | User Input Page | Page to upload legacy code and specify framework | 6
|  | Output Viewer | Display AI-generated modernized code | 6
|  | API Integration | Call backend services for transformation | 4
3 | Backend Development | FastAPI Setup | Environment setup, folder structure | 4
|  | Upload & Parse Legacy Code | Accept code, extract structure | 6
|  | AI Integration Logic | Prompt creation, sending to GPT/OpenAI API | 10
|  | Code Generator | Receive and store modernized code | 6
|  | Logging & Error Handling | Robustness & maintainability | 4
4 | AI Prompt Design & Optimization | Prompt Design | Effective prompt structure for legacy-to-modern conversion | 6
|  | Test & Tuning | Refine prompts for different legacy formats | 6
5 | Testing & Deployment | Unit Testing | Frontend & backend unit tests | 6
|  | Integration Testing | End-to-end flow test from upload to result | 6
|  | Dockerization | Containerize backend for portability | 4
|  | Deployment | Setup on cloud (e.g., Azure/AWS) | 6
6 | Documentation & Buffer | Technical Docs | README, architecture flow, API usage | 6
|  | User Guide | Guide for using the app effectively | 4
|  | Buffer | For unplanned changes/feedback | 6